## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Greeshma | 2026-01-12 | Initial dataset was highly sparse, resulting in weak recommendations and limited user-product interaction coverage. | Milestone 1 | Greeshma | Standards | Replaced the original sparse dataset with a denser, interaction-rich dataset to improve recommendation reliability. | 2026-01-13 | Closed | Implemented popular product-based recommendations for new users with session-level personalization.
2 | Greeshma | 2026-01-19 | Recommendations lacked relevance due to imbalance in user interaction signals | Milestone 2 | Greeshma | Logical | Introduced interaction-based weighting (view, add-to-cart, purchase) to prioritize meaningful user actions. | 2026-01-21 | Closed | Improved ranking of recommended products.
3 | Greeshma | 2026-01-26 | Purchased products were repeatedly shown in the recommendations list. | Milestone 3 | Greeshma | Logical | Added filtering logic to exclude already purchased items from recommendations. | 2026-01-26 | Closed | Enhanced post-purchase user experience.
4 | Greeshma | 2026-01-30 | Cold-start users received generic or empty recommendations on first login. | Milestone 3 | Greeshma | Logical | Added product name, description, price, and images to improve product visibility. | 2026-01-30 | Closed | UI became more informative and engaging.
5 | Greeshma | 2026-02-08 | Product listings lacked essential information, making the UI less user-friendly. | Milestone 4 | Greeshma | User Interface | Implemented character limits and responsive card styling to maintain uniform layout. | 2026-02-12 | Closed | Improved visual consistency across the app.
6 | Greeshma | 2026-02-20 | Inconsistent card sizes and long product names affected the layout of the application. | Milestone 4 | Greeshma | User Interface | Implemented popular product-based recommendations for new users with session-level personalization. | 2026-02-21 | Closed | Cold-start experience improved significantly.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others